## Main Sheet
Name | Date (start) | Date (end) | Hours worked | Description | Accounting Fix Comment
// General In class time... | .. |  | 0 | ..comment line.. |  |  |  | // .. means comment line
ALL | 2023-04-17 | 2023-04-17 | 0 | Dev Log + brainstorming (1.75hrs * 4) | Time moved to Digital Prototypes
Malachi | 2023-04-18 | 2023-04-18 | 0 | Art/music ideas | Time moved to Digital Prototypes
ALL | 2023-04-19 | 2023-04-19 | 0 | Dev Log + brainstorming (1hr *4) | Time moved to Digital Prototypes |  |  | Name ALL = all team members
ALL | 2023-04-21 | 2023-04-21 | 0 | Dev log (1hr *4) | Time moved to Digital Prototypes
Malachi | 2023-04-23 | 2023-04-23 | 0 | Researched FamiTracker for making 8 bit songs + wrote short motif | Time moved to Digital Prototypes
ALL | 2023-04-24 | 2023-04-24 | 0 | Dev log (1hr *4) | Time moved to Digital Prototypes
ALL | 2023-04-26 | 2023-04-26 | 0 | Dev log (1hr *4) | Time moved to Digital Prototypes |  |  | NOTE: For DevLog items, the time calculation is more for time working on those items in class more than the manhours actually needed to document that work...
ALL | 2023-05-01 | 2023-05-01 | 0 | Dev log (1hr *4) | Time moved to Digital Prototypes
All | 2023-05-03 | 2023-05-03 | 0 | Devlog (1hr * 4). Alpha work starts here... | Time moved to Alpha Build
All | 2023-05-08 | 2023-05-08 | 0 | DevLog (1.5hr * 4) | Time moved to Alpha Build
Jeff, lawrence, Malachi | 2023-05-10 | 2023-05-10 | 0 | DevLog (1hr * 3) | Time moved to Beta Build
Jeff, lawrence, Malachi | 2023-05-15 | 2023-05-15 | 0 | DevLog (2hr *3) | Time moved to Beta Build
ALL | 2023-05-22 | 2023-05-22 | 0 | Post Mortem, Planning, Merging, Playtesting 1.5 hoiurs each, counted individually around line 42-45 | Already acknowledged. no time to move here...
Total Time
//Extra time documenting | .. | .. | 0 | ..comment line.. |  |  | 228.85
.. | .. | .. | 0 | All of these moved to correct DevLog sections... | ..
// Digital Prototypes | .. |  | 0 | ..comment line
Lawrence | 2023-04-18 | 2023-04-30 | 11 |  | Will include both in class and out of class time
Jeffrey | 2023-04-22 | 2023-04-28 | 16.35 | 6.75 in-class + 9.6 out-of-class | Will include both in class and out of class time
Malachi | 2023-04-26 | 2023-04-28 | 7.5 |  | Will include both in class and out of class time
Joseph | 2023-04-26 | 2023-04-28 | 11 |  | Will include both in class and out of class time
//Alpha Build | .. | .. | 0 | ..comment line..
Lawrence | 2023-05-03 | 2023-05-07 | 11 | Integrated piston into build with jump and made my level | Will include both in class and out of class time
Jeffrey | 2023-05-05 | 2023-05-05 | 12.5 | 2.5 in-class + 10 out-of-class | Will include both in class and out of class time
Malachi | 2023-05-05 | 2023-05-08 | 9.5 | 5 hours friday, 2 hours monday | Will include both in class and out of class time
Joseph | 2023-05-01 | 2023-05-07 | 10.5 | artwork in progress | Will include both in class and out of class time
//Beta Build | .. | .. | 0 | ..comment line..
Lawrence | 2023-05-10 | 2023-05-14 | 11 | Created menus for the game and made the website | Will include both in class and out of class time
Jeffrey | 2023-05-10 | 2023-05-14 | 8.5 | 3 in-class + 5.5 out-of-class | Will include both in class and out of class time
Malachi | 2023-05-10 | 2023-05-10 | 5 | physics + new level, created branch, needs to be integrated | Will include both in class and out of class time
Joseph | 2023-05-14 | 2023-05-14 | 8 | full autoscrolling prototype for beta testing | Will include both in class and out of class time
//Postmortem presentation | .. | .. | 0 | ..comment line..
Lawrence | 2023-05-18 | 2023-05-22 | 15.75 | Main task was creating the boss level | Will include both in class and out of class time
Jeffrey | 2023-05-17 | 2023-05-24 | 14 | 5.5 in-class + 8.5 out-of-class | Will include both in class and out of class time | // [question from malachi] is this 10 number personal, or does this include all our combined time for the meeting on monday 5/22?
Malachi | 2023-05-17 | 2023-05-22 | 15.5 | 1 hour friday, 5 hours of sound design sunday, 4 hours sound design + implementation Monday, 1.5 hrs during classtime meeting | Will include both in class and out of class time
Joseph | 2023-05-17 | 2023-05-22 | 15 | touching up assets and levels, presentation slides, meetings | Will include both in class and out of class time
//Game Presentation | .. | .. | 0 | ..comment line..
Lawrence | 2023-05-24 | 2023-05-30 | 12.5 | A lot of small tweaks and bug fixes as well as work on the website | Will include both in class and out of class time
Jeffrey | 2023-05-25 | 2023-05-31 | 6.5 | 3.75 in-class + 2.75 out-of-class | Will include both in class and out of class time
Malachi | 2023-05-29 | 2023-05-30 | 5 | editing game trailer | Will include both in class and out of class time
Joseph | 2023-05-24 | 2023-05-30 | 6.5 | presentation slides | Will include both in class and out of class time
//Final Deliverables | .. | .. | 0 | ..comment line..
Lawrence | 2023-06-02 | 2023-06-04 | 4 | approx 4 | Will include both in class and out of class time
Jeffrey | 2023-06-02 | 2023-06-04 | 5.25 |  | Will include both in class and out of class time
Malachi | 2023-06-02 | 2023-06-04 | 4 |  | Will include both in class and out of class time
Joseph | 2023-06-02 | 2023-06-04 | 3 |  | Will include both in class and out of class time
//Cumulative Total | .. | .. | 228.85 | .. | ..